## ACTIVE CONTRACTS
CONTRACT REGISTER AS AT 31 DECEMBER 2024
No | Name of Service Provider | Bid/ Contract Number | Description of Service | Contract Amount | Contract Period | Start Date | End Date | Extension | Expenditure | Variation | Penalties Paid by Municipality / Impose by or Contractor | Contract Ammendment Date | Comment
1 | Munsoft (Pty) Ltd | Transversal Contract | Provision and maintenance of financial system | As per quoted amount | 36 | 31/5/2019 | 30/6/2022 | 30/6/2025 | 14081854.1 | None | None | None | Contract extension noted by council . Notice for public comments are closing on the 4th February 2025
2 | Matshego Engineers | THLM/SCM03/2019-2020/TS1B | Panel of consulting engineering firms for the implementation of water projects projects for a period of 36 months (Tweefontein Dk water Infrastructure) Upgrading of Tweefontein K Waste Water Treatment Works, Phase 2 | Based on fixed 7 % | 36 | 25/9/2019 | 24/9/2022 | 30/6/2025 | 5101702.33 | None | None | None | Contract Extended
3 | Monde Consulting Engineers | THLM/SCM03/2019-2020/TS1F | Panel of consulting enginering firms for the implementation for sanitation projects for a period of 36 months (Altenative Sanitation Systems) | Based on quoted rates of 8% | 36 | 25/9/2019 | 24/9/2022 | 30/6/2025 | 1144489.64 | None | None | None | Contract Extended
4 | City of Tshwane | Public Entity | Bulk water supply | Rates | 36 | 01/09/2023 | 31/08/2026 | N/A | 18944693.35 | None | None | None | Active
5 | Rand Water | Public Entity | Bulk water supply | Rates | 36 | Long Term Contract |  | To infinity | 667784110.37 | None | None | None | Contract Extended (Infinite Contract)
6 | Matupunuka ICT (Pty) Ltd | THLM/SCM08/2021-2022/ICT01 | Supply, delivery and maintenance of 3rd level support in all ICT matters for a period of 36 months and Telemetry System | R375 066.55 per month | 36 | 18/5/2022 | 17/5/2025 | N/A | 29626567.65 | None | None | None | Active
7 | Jasino General Services | THLM/SCM01/2022-2023/RS01 | Appointment of a panel of routine road maintenance in all Thembisile Hani Local Municipality wards, as and when required for a period of 36 Months | As per negotiated and accepted rates | 36 | 16/1/2023 | 15/1/2026 | N/A | 10238102.89 | None | None | None | Active
8 | Mandla Kasokobe General Trading | THLM/SCM01/2022-2023/RS01 | Appointment of a panel of routine road maintenance in all Thembisile Hani Local Municipality wards, as and when required for a period of 36 Months | As per negotiated and accepted rates | 36 | 16/1/2023 | 15/1/2026 | N/A | 4819809.66 | None | None | None | Active
9 | Oradimpho Business Enterprise | THLM/SCM01/2022-2023/RS01 | Appointment of a panel of routine road maintenance in all Thembisile Hani Local Municipality wards, as and when required for a period of 36 Months | As per negotiated and accepted rates | 36 | 16/1/2023 | 15/1/2026 | N/A | R 2 065 546.00 | None | None | None | Active
10 | Elezulu Construction and | THLM/SCM01/2022-2023/RS01 | Appointment of a panel of routine road maintenance in all Thembisile Hani Local Municipality wards, as and when required for a period of 36 Months | As per negotiated and accepted rates | 36 | 16/1/2023 | 15/1/2026 | N/A | 5818452.56 | None | None | None | Active
11 | Mpisana Properties | THLM/SCM01/2022-2023/RS01 | Appointment of a panel of routine road maintenance in all Thembisile Hani Local Municipality wards, as and when required for a period of 36 Months | As per negotiated and accepted rates | 36 | 16/1/2023 | 15/1/2026 | N/A | R 4,406,175.39 | None | None | None | Active
12 | Stickson General Trading | THLM/SCM01/2022-2023/RS01 | Appointment of a panel of routine road maintenance in all Thembisile Hani Local Municipality wards, as and when required for a period of 36 Months | As per negotiated and accepted rates | 36 | 16/1/2023 | 15/1/2026 | N/A | 4227301.9 | None | None | None | Active
13 | Zondiwe Construction | THLM/SCM01/2022-2023/RS01 | Appointment of a panel of routine road maintenance in all Thembisile Hani Local Municipality wards, as and when required for a period of 36 Months | As per negotiated and accepted rates | 36 | 16/1/2023 | 15/1/2026 | N/A | 21687837.77 | None | None | None | Active
14 | Makhambavele Building & Construction | THLM/SCM01/2022-2023/RS01 | Appointment of a panel of routine road maintenance in all Thembisile Hani Local Municipality wards, as and when required for a period of 36 Months | As per negotiated and accepted rates | 36 | 16/1/2023 | 15/1/2026 | N/A | 4184594 | None | None | None | Active
15 | Esinenhlanhla Logistics and Projects | THLM/SCM01/2022-2023/RS01 | Appointment of a panel of routine road maintenance in all Thembisile Hani Local Municipality wards, as and when required for a period of 36 Months | As per negotiated and accepted rates | 36 | 16/1/2023 | 15/1/2026 | N/A | 5352907.62 | None | None | None | Active
16 | KIS and Masemanku JV | THLM/SCM01/2022-2023/RS01 | Appointment of a panel of routine road maintenance in all Thembisile Hani Local Municipality wards, as and when required for a period of 36 Months | As per negotiated and accepted rates | 36 | 16/1/2023 | 15/1/2026 | N/A | 5180506.47 | None | None | None | Active
17 | Somthwalo Construction | THLM/SCM01/2022-2023/RS01 | Appointment of a panel of routine road maintenance in all Thembisile Hani Local Municipality wards, as and when required for a period of 36 Months | As per negotiated and accepted rates | 36 | 16/1/2023 | 15/1/2026 | N/A | 4112255 | None | None | None | Active
18 | Shumba Inc. (Pty) Ltd | THLM/SCM02/2022-2023/RISK01 | Appointment of a panel of forensic investigators to conduct investigations into allegations of fraud and corruption for a period of 36 Months | As per negotiated and accepted rates | 36 | 14/2/2023 | 13/2/2026 | N/A | R0.00 | None | None | None | Active
19 | Besalca Tax and Advisory (Pty) Ltd | THLM/SCM02/2022-2023/RISK01 | Appointment of a panel of forensic investigators to conduct investigations into allegations of fraud and corruption for a period of 36 Months | As per negotiated and accepted rates | 36 | 14/2/2023 | 13/2/2026 | N/A | 207000 | None | None | None | Active
20 | Manakana Risk and Advisory Services (Pty) Ltd | THLM/SCM02/2022-2023/RISK01 | Appointment of a panel of forensic investigators to conduct investigations into allegations of fraud and corruption for a period of 36 Months | As per negotiated and accepted rates | 36 | 14/2/2023 | 13/2/2026 | N/A | R0.00 | None | None | None | Active
21 | Jenny Internet | THLM/SCM11/2022-2023/ICT01 | Appointment for the supply of WAN, Internet and Telephone Management solutions to THLM for a period of 36 months | R 5 777 206.56 (excluding 15% VAT) | 36 | 31/3/2023 | 30/3/2026 | N/A | 2617773 | None | None | None | Active
22 | S & D Consulting Engineers (Pty) Ltd | THLM/SCM07/2022-23/E01 | Appointment of a panel of eletrical contractors for electrification on householdsl within THLM (Mafishane) | Negotiated and accepted rates as per the attached Bill of Quantities | 36 | 2023-03-07 | 2026-03-06 | N/A | 3238321.09 | None | None | None | Active
23 | S & D Consulting Engineers (Pty) Ltd | THLM/SCM07/2022-23/E01 | Appointment of a panel of eletrical contractors for electrification on householdsl within THLM (Magodongo) |  |  |  |  | N/A | 3071891.03 | None | None | None | Active
24 | Mahlatji Mmetji Trading and Projects | THLM/SCM07/2022-23/E01 | Appointment of a panel of eletrical contractors for electrification on householdsl within THLM (Mafishane) | R 3 035 046.83 (Including VAT) | 36 | 2023-03-07 | 2026-03-06 | N/A | 2868435.97 | None | None | None | Active
25 | Rampserv Consulting (Pty) Ltd | THLM/SCM07/2022-23/E01 | Appointment of a panel of eletrical contractors for electrification on householdsl within THLM (Magodongo) | R 1 976 641.61 (Including VAT) | 36 | 2023-03-07 | 2026-03-06 | N/A | 2919147.31 | None | None | None | Active
26 | NGHR Building Construction (Pty) Ltd | THLM/SCM07/2022-23/E01 | Appointment of a panel of eletrical contractors for electrification on householdsl within THLM (Magodongo) | R 1 926 522.73 (Including VAT) | 36 | 2023-03-07 | 2026-03-06 | N/A | R 2 937 479.86 | None | None | None | Active
27 | M Cube Engineering Technical Services | THLM/SCM07/2022-23/E01 | Appointment of a panel of eletrical contractors for electrification on householdsl within THLM (Magodongo) | R 4 393 364.00 (Including VAT) | 36 | 2023-03-07 | 2026-03-06 | N/A | R 3 697 335.98 | None | None | None | Active
28 | Gambani Royal Investment (Pty) Ltd | THLM/SCM09/2022-2023/LO1 | Panel for the provision of professional legal,advisory, governance, compliance and regulatory servives for Thembisile Hani Local Municipality as and when required for a period of 36 months | Based on negotiated rates | 36 | 2023-05-04 | 2026-04-04 | N/A | R0.00 | None | None | None | Active
29 | NG Dlamini Attorneys | THLM/SCM09/2022-2023/LO1 | Panel for the provision of professional legal,advisory, governance, compliance and regulatory servives for Thembisile Hani Local Municipality as and when required for a period of 36 months | Based on negotiated rates | 36 | 2023-05-04 | 2026-04-04 | N/A | R 124 959.86 | None | None | None | Active
30 | Kambonane Cooper Inc. | THLM/SCM09/2022-2023/LO1 | Panel for the provision of professional legal,advisory, governance, compliance and regulatory servives for Thembisile Hani Local Municipality as and when required for a period of 36 months | Based on negotiated rates | 36 | 2023-05-04 | 2026-04-04 | N/A | 111831.76 | None | None | None | Active
31 | Kubheka Siphesihle Attorneys | THLM/SCM09/2022-2023/LO1 | Panel for the provision of professional legal,advisory, governance, compliance and regulatory servives for Thembisile Hani Local Municipality as and when required for a period of 36 months | Based on negotiated rates | 36 | 2023-05-04 | 2026-04-04 | N/A | R 0.00 | None | None | None | Active
32 | Mphokane Attorneys | THLM/SCM09/2022-2023/LO1 | Panel for the provision of professional legal,advisory, governance, compliance and regulatory servives for Thembisile Hani Local Municipality as and when required for a period of 36 months | Based on negotiated rates | 36 | 2023-05-04 | 2026-04-04 | N/A | R 0.00 | None | None | None | Active
33 | Nkgadima Associates and Attorneys Inc. | THLM/SCM09/2022-2023/LO1 | Panel for the provision of professional legal,advisory, governance, compliance and regulatory servives for Thembisile Hani Local Municipality as and when required for a period of 36 months | Based on negotiated rates | 36 | 2023-05-04 | 2026-04-04 | N/A | 81490.15 | None | None | None | Active
34 | PK Legodi Incorporated | THLM/SCM09/2022-2023/LO1 | Panel for the provision of professional legal,advisory, governance, compliance and regulatory servives for Thembisile Hani Local Municipality as and when required for a period of 36 months | Based on negotiated rates | 36 | 2023-05-04 | 2026-04-04 | N/A | 4442446 | None | None | None | Active
35 | Zitho Trading T/A Zitho Travel | THLM/SCM16/2022-2023/C02 | Provision of Travel (flights and car hire), accommodation and venue hire services for a period of 36 months | Based on negotiated rates | 36 | 2023-05-04 | 2026-04-04 | N/A | 5102538.25 | None | None | None | Active
36 | Mhangana Fleet Management | THLM/SCM16/2022-2023/C02 | Service provider to provide vehicle tracking and monitoring system for a period of 36 months | R 3 083 035.00 excluding 15% Value Added Tax (VAT) | 36 | 2023-11-04 | 2026-10-04 | None | 1274733.55 | None | None | None | Active
37 | MFTP Snappy JV | THLM/SCM08/2022-23/RS01 | Panel of Contractors for Rehabilitation of Road Infrastructure as and when Required for a Period of 36 Months | Negotiated and accepted rates as per the attached Bill of Quantities | 36 | 20/4/2023 | 19/4/2026 | N/A | 3915661.77 | None | None | None | Active
38 | Little Rocky Development Projects | THLM/SCM08/2022-23/RS01 | Panel of Contractors for Rehabilitation of Road Infrastructure as and when Required for a Period of 36 Months | Negotiated and accepted rates as per the attached Bill of Quantities | 36 | 20/4/2023 | 19/4/2026 | N/A | R0.00 | None | None | None | Active
39 | Maphosa Helman Trading and Projects | THLM/SCM08/2022-23/RS01 | Panel of Contractors for Rehabilitation of Road Infrastructure as and when Required for a Period of 36 Months | Negotiated and accepted rates as per the attached Bill of Quantities | 36 | 20/4/2023 | 19/4/2026 | N/A | 4991500.09 | None | None | None | Active
40 | Kuye Trading. | THLM/SCM08/2022-23/RS01 | Panel of Contractors for Rehabilitation of Road Infrastructure as and when Required for a Period of 36 Months | Negotiated and accepted rates as per the attached Bill of Quantities | 36 | 20/4/2023 | 19/4/2026 | N/A | R0.00 | None | None | None | Active
41 | Lilotaki Construction (Pty) Ltd | THLM/SCM08/2022-23/RS01 | Panel of Contractors for Rehabilitation of Road Infrastructure as and when Required for a Period of 36 Months | Negotiated and accepted rates as per the attached Bill of Quantities | 36 | 20/4/2023 | 19/4/2026 | N/A | R0.00 | None | None | None | Active
42 | Thumasha Electrical Electronic and Water Supplier | THLM/SCM08/2022-23/RS01 | Panel of Contractors for Rehabilitation of Road Infrastructure as and when Required for a Period of 36 Months | Negotiated and accepted rates as per the attached Bill of Quantities | 36 | 20/4/2023 | 19/4/2026 | N/A | R 4 330 344.29 | None | None | None | Active
43 | Bogolo Waste Management and Projects | THLM/SCM08/2022-23/RS01 | Panel of Contractors for Rehabilitation of Road Infrastructure as and when Required for a Period of 36 Months | Negotiated and accepted rates as per the attached Bill of Quantities | 36 | 20/4/2023 | 19/4/2026 | N/A | R0.00 | None | None | None | Active
44 | Moeding Wadiphiri Trading and Projects | THLM/SCM08/2022-23/RS01 | Panel of Contractors for Rehabilitation of Road Infrastructure as and when Required for a Period of 36 Months | Negotiated and accepted rates as per the attached Bill of Quantities | 36 | 20/4/2023 | 19/4/2026 | N/A | 4228997.66 | None | None | None | Active
45 | DKPB Civil Engineering Contractors | THLM/SCM08/2022-23/RS01 | Panel of Contractors for Rehabilitation of Road Infrastructure as and when Required for a Period of 36 Months | Negotiated and accepted rates as per the attached Bill of Quantities | 36 | 20/4/2023 | 19/4/2026 | N/A | 2172738.58 | None | None | None | Active
46 | Chipane One Body JV | THLM/SCM08/2022-23/RS01 | Panel of Contractors for Rehabilitation of Road Infrastructure as and when Required for a Period of 36 Months | Negotiated and accepted rates as per the attached Bill of Quantities | 36 | 20/4/2023 | 19/4/2026 | N/A | 5900872.85 | None | None | None | Active
47 | Irhalane Construction | THLM/SCM08/2022-23/RS01 | Panel of Contractors for Rehabilitation of Road Infrastructure as and when Required for a Period of 36 Months | Negotiated and accepted rates as per the attached Bill of Quantities | 36 | 20/4/2023 | 19/4/2026 | N/A | 4098815.2 | None | None | None | Active
48 | Rhuone Projects | THLM/SCM018/2022-23/E03 | Implementation of Energy Efficiency and Demand Side Management (EEDSM) Program | R 1 000 000.00 (Vat Excluding Vat) | 36 | 23/5/2023 | 22/5/2026 | N/A | 2936634.67 | None | None | None | Active
49 | Reliant | THLM/SCM018/2022-23/E03 | Implementation of Energy Efficiency and Demand Side Management (EEDSM) Program | R 1 000 000.00 (Vat Exclusive) | 36 | 23/5/2023 | 22/5/2026 | N/A | 2615119.52 | None | None | None | Active
50 | MTK 3 Trading and Projrcts | THLM/SCM018/2022-23/E03 | Implementation of Energy Efficiency and Demand Side Management (EEDSM) Program | R 1 000 000.00 (Vat Exclusive) | 36 | 23/5/2023 | 22/5/2026 | N/A | R 1 302 608.20 | None | None | None | Active
51 | ADI Africa | THLM/SCM013/2022-23/E02 | Installation of High Mast Lights in Various Villages | Based on quoted rates of 6% | 36 | 23/5/2023 | 22/5/2026 | N/A | 78800 | None | None | None | Active
52 | Rhuone Projects | THLM/SCM013/2022-23/E02 | Installation of High Mast Lights as and when required for a Period of 36 Months | R 1 000 000.00 ( Excluding Vat) | 36 | 23/5/2023 | 22/5/2026 | N/A | R 1 784 275.00 | None | None | None | Active
53 | Reliant Consulting JV Thaps Electrical | THLM/SCM013/2022-23/E02 | Appointment of a panel of electrical contractors for the supply, delivery and installation of high mast lights as and when required for a period of 36 months (Mafishane) and Highmast Lights | Based on quoted rates of 8% | 36 | 23/5/2023 | 22/5/2026 | N/A | 4534240.22 | None | None | None | Active
54 | S & D Consulting Engineers (Pty) Ltd | THLM/SCM013/2022-23/E02 | Installation of High Mast Lights in Various Villages | R 1 725 000.00 (Including Vat) | 36 | 23/5/2023 | 22/5/2026 | N/A | 2614115.82 | None | None | None | Active
55 | Star Jays Ezimtoti JV | THLM/SCM013/2022-23/E02 | Appointment of a panel of electrical contractors for the supply, delivery and installation of high mastlights as and when required for a period of 36 months | Based on quoted rates of 8% | 36 | 23/5/2023 | 22/5/2026 | N/A | R 0.00 | None | None | None | Active
56 | Nghilazi Group (Pty) Ltd | THLM/SCM013/2022-23/E02 | Appointment of a panel of electrical contractors for the supply, delivery and installation of high mast lights as and when required for a period of 36 months | Based on quoted rates of 8% | 36 | 23/5/2023 | 22/5/2026 | N/A | R 0.00 | None | None | None | Active
57 | Lesedi La Balomo Business Enterprise | THLM/SCM013/2022-23/E02 | Appointment of a panel of electrical contractors for the supply, delivery and installation of high mast lights as and when required for a period of 36 months | Based on quoted rates of 8% | 36 | 23/5/2023 | 22/5/2026 | N/A | 4791180.39 | None | None | None | Active
58 | Nedbank Limited (Pty) Ltd | THLM/SCM15/2022-2023/BTO 01 | Provision of banking services for THLM for a period of 36 months | Based on quoted rates of 8% | 60 | 2023-01-06 | 2028-01-05 | N/A | R 0.00 | None | None | None | Active
59 | Nomsukazi JV | THLM/SCM20/2022-2023/RS05 | Supply and Delivery of Roads and Stormwater Materials as and when Required for a Period of 36 Months | Negotiated and accepted rates | 36 | 2023-07-06 | 2026-06-06 | N/A | 753510.4 | None | None | None | Active
60 | Thula Sizwe Trading cc | THLM/SCM20/2022-2023/RS05 | Supply and Delivery of Roads and Stormwater Materials as and when Required for a Period of 36 Months | Negotiated and accepted rates | 36 | 2023-07-06 | 2026-06-06 | N/A | 2868305.38 | None | None | None | Active
61 | Saint 4 Trading and Projects | THLM/SCM20/2022-2023/RS05 | Supply and Delivery of Roads and Stormwater Materials as and when Required for a Period of 36 Months | Negotiated and accepted rates | 36 | 2023-07-06 | 2026-06-06 | N/A | 735632 | None | None | None | Active
62 | Sithabesoke JV Muhlebuyi | THLM/SCM20/2022-2023/RS05 | Supply and Delivery of Roads and Stormwater Materials as and when Required for a Period of 36 Months | Negotiated and accepted rates | 36 | 2023-07-06 | 2026-06-06 | N/A | 1835509.6 | None | None | None | Active
63 | TNK and Mokobi Sir (Pty) Ltd | THLM/SCM20/2022-2023/RS05 | Supply and Delivery of Roads and Stormwater Materials as and when Required for a Period of 36 Months | Negotiated and accepted rates | 36 | 2023-07-06 | 2026-06-06 | N/A | 1471558.8 | None | None | None | Active
64 | Isipho Sikadumeleni (PTY) LTD | THLM/SCM20/2022-2023/RS06 | Supply and Delivery of Roads and Stormwater Materials as and when Required for a Period of 36 Months | Negotiated and accepted rates | 36 | 2023-07-06 | 2026-06-06 | N/A | 893856 | None | None | None | Active
65 | Wandisile Business Enterprise | THLM/SCM19/2022-2023/E04 | Supply and Delivery of Electrical Materials as and when Required for a Period of 36 Months | Negotiated and accepted rates | 36 | 2023-07-06 | 2026-06-06 | N/A | R 145 312.62 | None | None | None | Active
66 | Indlhovukazi Masimula Mnisi JV | THLM/SCM19/2022-2023/E04 | Supply and Delivery of Electrical Materials as and when Required for a Period of 36 Months | Negotiated and accepted rates | 36 | 2023-07-06 | 2026-06-06 | N/A | R 0.00 | None | None | None | Active
67 | NKZ Investment Group (PTY) LTD | THLM/SCM19/2022-2023/E04 | Supply and Delivery of Electrical Materials as and when Required for a Period of 36 Months | Negotiated and accepted rates | 36 | 2023-07-06 | 2026-06-06 | N/A | R 254 363.23 | None | None | None | Active
68 | Artsosgay (Pty) Ltd | THLM/SCM19/2022-2023/E04 | Supply and Delivery of Electrical Materials as and when Required for a Period of 36 Months | Negotiated and accepted rates | 36 | 2023-07-06 | 2026-06-06 | N/A | 563042.76 | None | None | None | Active
69 | Masemanku Trading and Projects | THLM/SCM19/2022-2023/E04 | Supply and Delivery of Electrical Materials as and when Required for a Period of 36 Months | Negotiated and accepted rates | 36 | 2023-07-06 | 2026-06-06 | N/A | 215990.16 | None | None | None | Active
70 | SS Max | THLM/SCM19/2022-2023/E04 | Supply and Delivery of Electrical Materials as and when Required for a Period of 36 Months | Negotiated and accepted rates | 36 | 2023-07-06 | 2026-06-06 | N/A | 778590.77 | None | None | None | Active
71 | Noponde Business Enterprise | THLM/SCM26/2022-2023/WS02 | Appointment of a contractor for the upgrading of Tweefontein K Waste Water Treatment Works, Phase2-Water and Sewer Reticulation Works-Work Package 1 | R27 963 053.16 (Including 15% Vat and 10% Contigencies | 36 | 2023-08-06 | 2026-07-06 | N/A | 6624199.93 | None | None | None | Active
72 | Qubic Africa Joint venture | THLM/SCM10/2022-23/TSC01 | Appointment of a panel of engineering firms for the implementation of infrastructure projects for THLM as and when required for a period of 36 months | Based on quoted rates of 8% | 36 | 15/6/2023 | 14/6/2026 | N/A | R 0.00 | None | None | None | Active
73 | Pule Ramasimong Consultants | THLM/SCM10/2022-23/TSC01 | Appointment of a panel of engineering firms for the implementation of infrastructure projects for THLM as and when required for a period of 36 months | Based on quoted rates of 8% | 36 | 15/6/2023 | 14/6/2026 | N/A | R 0.00 | None | None | None | Active
74 | Rhandzo Projects (Pty) Ltd | THLM/SCM10/2022-23/TSC01 | Appointment of a panel of engineering firms for the implementation of infrastructure projects for THLM as and when required for a period of 36 months | Based on quoted rates of 8% | 36 | 15/6/2023 | 14/6/2026 | N/A | R 0.00 | None | None | None | Active
75 | Dikgato Engineering Consultants (Pty) Ltd | THLM/SCM10/2022-23/TSC01 | Appointment of a panel of engineering firms for the implementation of infrastructure projects for THLM as and when required for a period of 36 months Mahlabathini | Based on quoted rates of 8% | 36 | 15/6/2023 | 14/6/2026 | N/A | 3260846.42 | None | None | None | Active
76 | Thoko Consulting Engineering (Pty) Ltd | THLM/SCM10/2022-23/TSC01 | Appointment of a panel of engineering firms for the implementation of infrastructure projects for THLM as and when required for a period of 36 months | Based on quoted rates of 8% | 36 | 15/6/2023 | 14/6/2026 | N/A | 867005.21 | None | None | None | Active
77 | Warona Consulting Engineers | THLM/SCM10/2022-23/TSC01 | Appointment of a panel of engineering firms for the implementation of infrastructure projects for THLM as and when required for a period of 36 months | Based on quoted rates of 8% | 36 | 15/6/2023 | 14/6/2026 | N/A | 2923330.79 | None | None | None | Active
78 | AFI Consult (Pty) Ltd | THLM/SCM10/2022-23/TSC01 | Appointment of a panel of engineering firms for the implementation of infrastructure projects for THLM as and when required for a period of 36 months | Based on quoted rates of 8% | 36 | 15/6/2023 | 14/6/2026 | N/A | 989808.49 | None | None | None | Active
79 | NKP Consulting Engineers | THLM/SCM10/2022-23/TSC01 | Appointment of a panel of engineering firms for the implementation of infrastructure projects for THLM as and when required for a period of 36 months | Based on quoted rates of 8% | 36 | 15/6/2023 | 14/6/2026 | N/A | 1638640.1 | None | None | None | Active
80 | Hi End Group | THLM/SCM10/2022-23/TSC01 | Appointment of a panel of engineering firms for the implementation of infrastructure projects for THLM as and when required for a period of 36 months | Based on quoted rates of 8% | 36 | 15/6/2023 | 14/6/2026 | N/A | 517067.66 | None | None | None | Active
81 | ISAO Consulting | THLM/SCM10/2022-23/TSC01 | Appointment of a panel of engineering firms for the implementation of infrastructure projects for THLM as and when required for a period of 36 months | Based on quoted rates of 8% | 36 | 15/6/2023 | 14/6/2026 | N/A | R 0.00 | None | None | None | Active
82 | RSZ Engineers and Projects | THLM/SCM10/2022-23/TSC01 | Appointment of a panel of engineering firms for the implementation of infrastructure projects for THLM as and when required for a period of 36 months | Based on quoted rates of 8% | 36 | 15/6/2023 | 14/6/2026 | N/A | 2160948.89 | None | None | None | Active
83 | Lihuzu Projects (Ltd) Pty | THLM/SCM10/2022-23/TSC01 | Appointment of a panel of engineering firms for the implementation of infrastructure projects for THLM as and when required for a period of 36 months | Based on quoted rates of 8% | 36 | 15/6/2023 | 14/6/2026 | N/A | R 0.00 | None | None | None | Active
84 | G Seal Consulting (Pty) Ltd | THLM/SCM10/2022-23/TSC01 | Appointment of a panel of engineering firms for the implementation of infrastructure projects for THLM as and when required for a period of 36 months | Based on quoted rates of 8% | 36 | 15/6/2023 | 14/6/2026 | N/A | R 0.00 | None | None | None | Active
85 | Mangadi solution (Pty) Ltd | THLM/SCM10/2022-23/TSC01 | Appointment of a panel of engineering firms for the implementation of infrastructure projects for THLM as and when required for a period of 36 months | Based on quoted rates of 8% | 36 | 15/6/2023 | 14/6/2026 | N/A | R 0.00 | None | None | None | Active
86 | Mot Pro Consultant Engineers (Pty) Ltd | THLM/SCM10/2022-23/TSC01 | Appointment of a panel of engineering firms for the implementation of infrastructure projects for THLM as and when required for a period of 36 months | Based on quoted rates of 8% | 36 | 15/6/2023 | 14/6/2026 | N/A | R 0.00 | None | None | None | Active
87 | Face Of Earth Consultants | THLM/SCM10/2022-23/TSC01 | Appointment of a panel of engineering firms for the implementation of infrastructure projects for THLM as and when required for a period of 36 months | Based on quoted rates of 8% | 36 | 15/6/2023 | 14/6/2026 | N/A | 1474618.55 | None | None | None | Active
88 | Aseda Consulting Engineers (PTY) LTD | THLM/SCM10/2022-23/TSC01 | Appointment of a panel of engineering firms for the implementation of infrastructure projects for THLM as and when required for a period of 36 months | Based on quoted rates of 8% | 36 | 15/6/2023 | 14/6/2026 | N/A | R 0.00 | None | None | None | Active
89 | Esquare Engineering | THLM/SCM10/2022-23/TSC01 | Appointment of a panel of engineering firms for the implementation of infrastructure projects for THLM as and when required for a period of 36 months | Based on quoted rates of 8% | 36 | 15/6/2023 | 14/6/2026 | N/A | R 0.00 | None | None | None | Active
90 | King And Associates Engineering & project Managers (Pty) Ltd | THLM/SCM10/2022-23/TSC01 | Appointment of a panel of engineering firms for the implementation of infrastructure projects for THLM as and when required for a period of 36 months | Based on quoted rates of 8% | 36 | 15/6/2023 | 14/6/2026 | N/A | 3770398.3 | None | None | None | Active
91 | On Board Consulting Engineers (Pty) Ltd | THLM/SCM10/2022-23/TSC01 | Appointment of a panel of engineering firms for the implementation of infrastructure projects for THLM as and when required for a period of 36 months | Based on quoted rates of 8% | 36 | 15/6/2023 | 14/6/2026 | N/A | R 0.00 | None | None | None | Active
92 | MSB Consulting Engineers | THLM/SCM10/2022-23/TSC01 | Appointment of a panel of engineering firms for the implementation of infrastructure projects for THLM as and when required for a period of 36 months | Based on quoted rates of 8% | 36 | 15/6/2023 | 14/6/2026 | N/A | 1544192.38 | None | None | None | Active
93 | Ceenex (Pty) Ltd | THLM/SCM10/2022-23/TSC01 | Appointment of a panel of engineering firms for the implementation of infrastructure projects for THLM as and when required for a period of 36 months (Verena Water Infrastructure) | Based on quoted rates of 8% | 36 | 15/6/2023 | 14/6/2026 | N/A | 3252387 | None | None | None | Active
94 | Risima Project Management | THLM/SCM10/2022-23/TSC01 | Appointment of a panel of engineering firms for the implementation of infrastructure projects for THLM as and when required for a period of 36 months | Based on quoted rates of 8% | 36 | 15/6/2023 | 14/6/2026 | N/A | R 0.00 | None | None | None | Active
95 | Nzamakhuze Holdings (Pty) Ltd | THLM/SCM10/2022-23/TSC01 | Appointment of a panel of engineering firms for the implementation of infrastructure projects for THLM as and when required for a period of 36 months | Based on quoted rates of 8% | 36 | 15/6/2023 | 14/6/2026 | N/A | R 0.00 | None | None | None | Active
96 | Zenkon Engineers | THLM/SCM10/2022-23/TSC01 | Appointment of a panel of engineering firms for the implementation of infrastructure projects for THLM as and when required for a period of 36 months Oxidation | Based on quoted rates of 8% | 36 | 15/6/2023 | 14/6/2026 | N/A | 4848886.41 | None | None | None | Active
97 | Ceenex (Pty) Ltd | THLM/SCM10/2022-23/TSC01 | Panel of consulting engineering firms for the implementation of water projects projects for a period of 36 months (Water Conservation and Demand Mamanagement) | Based on quoted rates of 8% | 36 | 15/6/2023 | 14/6/2026 | N/A | 5928348.11 | None | None | None | Active
98 | Kabe Consulting Engineers | THLM/SCM10/2022-23/TSC01 | Appointment of a panel of engineering firms for the implementation of infrastructure projects for THLM as and when required for a period of 36 months | Based on quoted rates of 8% | 36 | 15/6/2023 | 14/6/2026 | N/A | R 0.00 | None | None | None | Active
99 | Best Thoughts Trading And Projects 358 cc | THLM/SCM10/2022-23/TSC01 | Appointment of a panel of engineering firms for the implementation of infrastructure projects for THLM as and when required for a period of 36 months | Based on quoted rates of 8% | 36 | 15/6/2023 | 14/6/2026 | N/A | R 0.00 | None | None | None | Active
100 | Mahlangu BEHR & Associates | THLM/SCM10/2022-23/TSC01 | Appointment of a panel of engineering firms for the implementation of infrastructure projects for THLM as and when required for a period of 36 months | Based on quoted rates of 8% | 36 | 15/6/2023 | 14/6/2026 | N/A | R 0.00 | None | None | None | Active
101 | Sejagobe Engineers CC | THLM/SCM10/2022-23/TSC01 | Appointment of a panel of engineering firms for the implementation of infrastructure projects for THLM as and when required for a period of 36 months | Based on quoted rates of 8% | 36 | 15/6/2023 | 14/6/2026 | N/A | 2000000 | None | None | None | Active
102 | TOBC Integrations (Pty) Ltd | THLM/SCM10/2022-23/TSC01 | Appointment of a panel of engineering firms for the implementation of infrastructure projects for THLM as and when required for a period of 36 months | Based on quoted rates of 8% | 36 | 15/6/2023 | 14/6/2026 | N/A | R 0.00 | None | None | None | Active
103 | Umshiya Security Services | THLM/SCM25/2022-2023/PED01 | Provision of assistance in handling evictions and relocation to counter land invasions for tha period of 36 months as and when required | Based on quoted rates of 8% | 36 | 18/7/2023 | 17/7/2026 | N/A | 203236.05 | None | None | None | Active
104 | Black Dot Property Consultants (Pty)Ltd | THLM/SCM28/2022-2023/BTO02 | Appointment of a service provider for the compilation and maintenance of the general valuation roll as well as the supply of other valuation related services in compliance with the municipal property rates ACT of 2004 | Negotiated rates | 36 | 31/8/2023 | 30/8/2026 | N/A | 7583498.02 | None | None | None | Active
105 | Tshwele Logistics | THLM/SCM29/2022-2023/WS03 | Appointment of a panel of contractors for rehabilitation, refurbishment and maintenance of water infrastructure for a period of 36 months(RRM & Boreholes) | Negotiated rates | 36 | 23/10/2023 | 22/10/2026 | None | 6783374.07 | None | None | None | Active
106 | Noponde Business Enterprise | THLM/SCM29/2022-2023/WS03 | Appointment of a panel of contractors for rehabilitation, refurbishment and maintenance of water infrastructure for a period of 36 months(RRM) | Negotiated rates | 36 | 23/10/2023 | 22/10/2026 | None | 821034.12 | N/A | None | None | Active
107 | Zwelpat Trading | THLM/SCM29/2022-2023/WS03 | Appointment of a panel of contractors for rehabilitation, refurbishment and maintenance of water infrastructure for a period of 36 months | Negotiated rates | 36 | 23/10/2023 | 22/10/2026 | None | 8553569.19 | N/A | None | None | Active
108 | Elezulu Construction | THLM/SCM29/2022-2023/WS03 | Appointment of a panel of contractors for rehabilitation, refurbishment and maintenance of water infrastructure for a period of 36 months(RRM & Oxidation) | Negotiated rates | 36 | 23/10/2023 | 22/10/2026 | None | 15580165.66 | N/A | None | None | Active
109 | Stickson General Trading (Pty) Ltd | THLM/SCM29/2022-2023/WS03 | Appointment of a panel of contractors for rehabilitation, refurbishment and maintenance of water infrastructure for a period of 36 months( Asbestos) and Ntokozweni | Negotiated rates | 36 | 23/10/2023 | 22/10/2026 | None | 7122893.1 | N/A | None | None | Active
110 | Zembeleni Transport and Projects | THLM/SCM29/2022-2023/WS03 | Appointment of a panel of contractors for rehabilitation, refurbishment and maintenance of water infrastructure for a period of 36 months | Negotiated rates | 36 | 23/10/2023 | 22/10/2026 | None | 2590352.49 | N/A | None | None | Active
111 | Ecotropers Construction | THLM/SCM29/2022-2023/WS03 | Appointment of a panel of contractors for rehabilitation, refurbishment and maintenance of water infrastructure for a period of 36 months | Negotiated rates | 36 | 23/10/2023 | 22/10/2026 | None | R 664 063.15 | N/A | None | None | Active
112 | Mulbert | THLM/SCM29/2022-2023/WS03 | Appointment of a panel of contractors for rehabilitation, refurbishment and maintenance of water infrastructure for a period of 36 months(RRM & Oxidation) | Negotiated rates | 36 | 23/10/2023 | 22/10/2026 | None | 8838881.81 | N/A | None | None | Active
113 | Fleet Horizon Solutions (Pty)Ltd | THLM/SCM08/2023-2024/F02 | Provision of Operatial Full Maintenance Vehicle Lease for a Period of 36 Months | R 44 853 942.60 excluding 15% Value Added Tax (VAT) | 36 | 15/11/2023 | 14/11/2026 | None | 6046634.65 | N/A | None | None | Active
114 | New Dawn Energy (Pty) Ltd | THLM/SCM07/2023-2024/F01 | Appointment of a Service Provider for Fueling and Supply of Lubricants for Municipal Fleet as and when Required for a Period of 36 Months | Negotiated rates | 36 | 18/12/2023 | 17/12/2026 | None | 13094245.82 | N/A | None | None | Active
115 | Carewell Holdings 5 (Pty) Ltd | THLM/SCM33/2022-2023/RISK03 | Appointment of Security Service Provider for a Period of 36 Months | Negotiated rates | 36 | 18/12/2023 | 17/12/2026 | None | 4783161.26 | N/A | None | None | Active
116 | Gubis 85 Solutions (Pty) Ltd | THLM/SCM33/2022-2023/RISK02 | Appointment of Security Service Provider for a Period of 36 Months | Negotiated rates | 36 | 18/12/2023 | 17/12/2026 | None | 6115800.98 | N/A | None | None | Active
117 | Asamalwandle Tradings | THLM/SCM30/2019-2020/WS04 | Panel of Temporary Water Supply through Water Tankers within Thembisile Hani Local Municipality as and when Required for a Period of 36 Months | Negotiated rates | 36 | 2024-09-01 | 2027-08-01 | None | 696150 | N/A | None | None | Active
118 | Azembelani Transport | THLM/SCM30/2019-2020/WS04 | Panel of Temporary Water Supply through Water Tankers within Thembisile Hani Local Municipality as and when Required for a Period of 36 Months | Negotiated rates | 36 | 2024-09-01 | 2027-08-01 | None | 628037.5 | N/A | None | None | Active
119 | Gangi Construction and Projects | THLM/SCM30/2019-2020/WS04 | Panel of Temporary Water Supply through Water Tankers within Thembisile Hani Local Municipality as and when Required for a Period of 36 Months | Negotiated rates | 36 | 2024-09-01 | 2027-08-01 | None | 1319532.25 | N/A | None | None | Active
120 | Gogtwana and Projects (Pty) Ltd | THLM/SCM30/2019-2020/WS04 | Panel of Temporary Water Supply through Water Tankers within Thembisile Hani Local Municipality as and when Required for a Period of 36 Months | Negotiated rates | 36 | 2024-09-01 | 2027-08-01 | None | 126990 | N/A | None | None | Active
121 | Green Horn Trading (Pty) Ltd | THLM/SCM30/2019-2020/WS04 | Panel of Temporary Water Supply through Water Tankers within Thembisile Hani Local Municipality as and when Required for a Period of 36 Months | Negotiated rates | 36 | 2024-09-01 | 2027-08-01 | None | 2894512.5 | N/A | None | None | Active
122 | Juluka Construction and Projects | THLM/SCM30/2019-2020/WS04 | Panel of Temporary Water Supply through Water Tankers within Thembisile Hani Local Municipality as and when Required for a Period of 36 Months | Negotiated rates | 36 | 2024-09-01 | 2027-08-01 | None | 514141 | N/A | None | None | Active
123 | Lungile Trading Enterprise | THLM/SCM30/2019-2020/WS04 | Panel of Temporary Water Supply through Water Tankers within Thembisile Hani Local Municipality as and when Required for a Period of 36 Months | Negotiated rates | 36 | 2024-09-01 | 2027-08-01 | None | 273861 | N/A | None | None | Active
124 | M90 Projects (Pty) Ltd | THLM/SCM30/2019-2020/WS04 | Panel of Temporary Water Supply through Water Tankers within Thembisile Hani Local Municipality as and when Required for a Period of 36 Months | Negotiated rates | 36 | 2024-09-01 | 2027-08-01 | None | 240948.5 | N/A | None | None | Active
125 | Mamakau Engineering | THLM/SCM30/2019-2020/WS04 | Panel of Temporary Water Supply through Water Tankers within Thembisile Hani Local Municipality as and when Required for a Period of 36 Months | Negotiated rates | 36 | 2024-09-01 | 2027-08-01 | None | 123372 | N/A | None | None | Active
126 | Mamolato Construction | THLM/SCM30/2019-2020/WS04 | Panel of Temporary Water Supply through Water Tankers within Thembisile Hani Local Municipality as and when Required for a Period of 36 Months | Negotiated rates | 36 | 2024-09-01 | 2027-08-01 | None | 1015128.3 | N/A | None | None | Active
127 | Mlotjwa Masters Trading Enterprise | THLM/SCM30/2019-2020/WS04 | Panel of Temporary Water Supply through Water Tankers within Thembisile Hani Local Municipality as and when Required for a Period of 36 Months | Negotiated rates | 36 | 2024-09-01 | 2027-08-01 | None | 832670 | N/A | None | None | Active
128 | Njani Projects | THLM/SCM30/2019-2020/WS04 | Panel of Temporary Water Supply through Water Tankers within Thembisile Hani Local Municipality as and when Required for a Period of 36 Months | Negotiated rates | 36 | 2024-09-01 | 2027-08-01 | None | R 0.00 | N/A | None | None | Active
129 | Nomabonga Enterprises | THLM/SCM30/2019-2020/WS04 | Panel of Temporary Water Supply through Water Tankers within Thembisile Hani Local Municipality as and when Required for a Period of 36 Months | Negotiated rates | 36 | 2024-09-01 | 2027-08-01 | None | 139263 | N/A | None | None | Active
130 | Nomzamo Enterprise (Pty) Ltd | THLM/SCM30/2019-2020/WS04 | Panel of Temporary Water Supply through Water Tankers within Thembisile Hani Local Municipality as and when Required for a Period of 36 Months | Negotiated rates | 36 | 2024-09-01 | 2027-08-01 | None | 134460 | N/A | None | None | Active
131 | P.J. Mahlangu Business Enterprises | THLM/SCM30/2019-2020/WS04 | Panel of Temporary Water Supply through Water Tankers within Thembisile Hani Local Municipality as and when Required for a Period of 36 Months | Negotiated rates | 36 | 2024-09-01 | 2027-08-01 | None | 407308.95 | N/A | None | None | Active
132 | Senzazona (Pty) Ltd | THLM/SCM30/2019-2020/WS04 | Panel of Temporary Water Supply through Water Tankers within Thembisile Hani Local Municipality as and when Required for a Period of 36 Months | Negotiated rates | 36 | 2024-09-01 | 2027-08-01 | None | 140910 | N/A | None | None | Active
133 | Sitjhebangani Transport | THLM/SCM30/2019-2020/WS04 | Panel of Temporary Water Supply through Water Tankers within Thembisile Hani Local Municipality as and when Required for a Period of 36 Months | Negotiated rates | 36 | 2024-09-01 | 2027-08-01 | None | 1281405.9 | N/A | None | None | Active
134 | Sokapo Transport Services | THLM/SCM30/2019-2020/WS04 | Panel of Temporary Water Supply through Water Tankers within Thembisile Hani Local Municipality as and when Required for a Period of 36 Months | Negotiated rates | 36 | 2024-09-01 | 2027-08-01 | None | 90330 | N/A | None | None | Active
135 | Somlungisi Transport | THLM/SCM30/2019-2020/WS04 | Panel of Temporary Water Supply through Water Tankers within Thembisile Hani Local Municipality as and when Required for a Period of 36 Months | Negotiated rates | 36 | 2024-09-01 | 2027-08-01 | None | 400650 | N/A | None | None | Active
136 | Vumsile Trading Enterprise | THLM/SCM30/2019-2020/WS04 | Panel of Temporary Water Supply through Water Tankers within Thembisile Hani Local Municipality as and when Required for a Period of 36 Months | Negotiated rates | 36 | 2024-09-01 | 2027-08-01 | None | 44640 | N/A | None | None | Active
137 | Amambokazi Trading & Projects | THLM/SCM30/2019-2020/WS05 | Panel of Temporary Water Supply through Water Tankers within Thembisile Hani Local Municipality as and when Required for a Period of 36 Months | Negotiated rates | 36 | 2024-09-01 | 2027-08-01 | None | 381077 | N/A | None | None | Active
138 | Hlehle Transport & Logistics | THLM/SCM30/2019-2020/WS06 | Panel of Temporary Water Supply through Water Tankers within Thembisile Hani Local Municipality as and when Required for a Period of 36 Months | Negotiated rates | 36 | 2024-09-01 | 2027-08-01 | None | 63000 | N/A | None | None | Active
139 | Kgosihadi Trading & Project | THLM/SCM30/2019-2020/WS07 | Panel of Temporary Water Supply through Water Tankers within Thembisile Hani Local Municipality as and when Required for a Period of 36 Months | Negotiated rates | 36 | 2024-09-01 | 2027-08-01 | None | 50760 | N/A | None | None | Active
140 | Khethakanye Trading and Projects | THLM/SCM30/2019-2020/WS08 | Panel of Temporary Water Supply through Water Tankers within Thembisile Hani Local Municipality as and when Required for a Period of 36 Months | Negotiated rates | 36 | 2024-09-01 | 2027-08-01 | None | 559450 | N/A | None | None | Active
141 | Makhonzela Futhi Trading | THLM/SCM30/2019-2020/WS09 | Panel of Temporary Water Supply through Water Tankers within Thembisile Hani Local Municipality as and when Required for a Period of 36 Months | Negotiated rates | 36 | 2024-09-01 | 2027-08-01 | None | 96390 | N/A | None | None | Active
142 | Maphosa Helman Trading and Projects | THLM/SCM30/2019-2020/WS10 | Panel of Temporary Water Supply through Water Tankers within Thembisile Hani Local Municipality as and when Required for a Period of 36 Months | Negotiated rates | 36 | 2024-09-01 | 2027-08-01 | None | 18646045.41 | N/A | None | None | Active
143 | Msana Bhoyi Construction and Projects | THLM/SCM30/2019-2020/WS11 | Panel of Temporary Water Supply through Water Tankers within Thembisile Hani Local Municipality as and when Required for a Period of 36 Months | Negotiated rates | 36 | 2024-09-01 | 2027-08-01 | None | 334894.5 | N/A | None | None | Active
144 | Mshonisi Trading and Projects | THLM/SCM30/2019-2020/WS12 | Panel of Temporary Water Supply through Water Tankers within Thembisile Hani Local Municipality as and when Required for a Period of 36 Months | Negotiated rates | 36 | 2024-09-01 | 2027-08-01 | None | 81972 | N/A | None | None | Active
145 | Prince Engineering and Projects | THLM/SCM30/2019-2020/WS13 | Panel of Temporary Water Supply through Water Tankers within Thembisile Hani Local Municipality as and when Required for a Period of 36 Months | Negotiated rates | 36 | 2024-09-01 | 2027-08-01 | None | R0.00 | N/A | None | None | Active
146 | Sihloniphile Trading and Construction | THLM/SCM30/2019-2020/WS14 | Panel of Temporary Water Supply through Water Tankers within Thembisile Hani Local Municipality as and when Required for a Period of 36 Months | Negotiated rates | 36 | 2024-09-01 | 2027-08-01 | None | 380283 | N/A | None | None | Active
147 | Somphambo Tranding and Enterprise | THLM/SCM30/2019-2020/WS15 | Panel of Temporary Water Supply through Water Tankers within Thembisile Hani Local Municipality as and when Required for a Period of 36 Months | Negotiated rates | 36 | 2024-09-01 | 2027-08-01 | None | 99774 | N/A | None | None | Active
148 | Chona Malanga Engineering CC | THLM/SCM31/2022-23/E06 | Panel of a consulting engineering firms for the implementation of electrical projects for Thembisile Hani Local Municipality as and when Required | Negotiated and accepted rates | 36 | 2024-11-01 | 2027-10-01 | None | 1590344.89 | N/A | None | None | Active
149 | Irhalane Costruction | THLM/SCM05/2023-2024/WS02 | Upgrading of Thembalethu Water Infrastructure Ward 05 | R 26 821 154.34 including Contingencies and Value Added Tax (VAT). | 36 | 18/1/2024 | 17/1/2027 | None | 7156940.85 | N/A | None | None | Active
150 | DKPB Construction (Pty) Ltd | THLM/SCM06/2023-2024 | Upgrading of Verena Water Infrastructure – Ward 08 | R 38 855 536.01 including Contingencies and VAT. | 36 | 18/1/2024 | 17/1/2027 | None | 8295148.57 | N/A | None | None | Active
151 | Tshedza Tshashu Industries | THLM/SCM25/2023-2024/PED01 | Appointment of a service providers for provision of events management services for Thembisile Hani Local Municipality for a period 36 months | Negotiated and accepted rates | 36 | 2024-05-02 | 2027-04-02 | None | 0 | N/A | None | None | Active
152 | ITR Sound (PTY) LTD | THLM/SCM25/2023-2024/PED01 | Appointment of a service providers for provision of events management services for Thembisile Hani Local Municipality for a period 36 months | Negotiated and accepted rates | 36 | 2024-05-02 | 2027-04-02 | None | 1430000 | N/A | None | None | Active
153 | PTP Intergrated (Pty) Ltd | THLM/SCM16/2023-2024/CS01 | Appointment of a service providers for provision, configuration, implementation, maintenance and support of workflow, document management, records management and scanning / indexing systems for a period 36 months | R 7 851 192.98 including 15% Value Added Tax (VAT). | 36 | 14/2/2024 | 13/2/2027 | None | 2619098.3 | N/A | None | None | Active
154 | Global Solution Development | THLM/SCM15/2023-24/TW01 | Appointment of a Panel of Town and Regional Planning Consultants to Provide Town and Regional Planning Services to Thembisile Hani Local Municipality as and when Required for a Period of 36 Months | As per negotiated and accepted rates | 36 | 28/2/2024 | 27/2/2027 | None | 141450 | N/A | None | None | Active
155 | Pfukani-Kusile Consulting | THLM/SCM15/2023-24/TW01 | Appointment of a Panel of Town and Regional Planning Consultants to Provide Town and Regional Planning Services to Thembisile Hani Local Municipality as and when Required for a Period of 36 Months | As per negotiated and accepted rates | 36 | 28/2/2024 | 27/2/2027 | None | R 0.00 | N/A | None | None | Active
156 | PMT Charted Accountants (Pty) Ltd | THLM/SCM24/2023-2024/AUD01 | Appointment of Audit firms for co-sourcing of internal audit projects for a period of 36 months | As per negotiated and accepted rates | 36 | 25/4/2024 | 24/4/2027 | None | R 0.00 | N/A | None | None | Active
157 | CHAPU CA | THLM/SCM24/2023-2024/AUD01 | Appointment of Audit firms for co-sourcing of internal audit projects for a period of 36 months | As per negotiated and accepted rates | 36 | 25/4/2024 | 24/4/2027 | None | R 0.00 | N/A | None | None | Active
158 | Mareketso Business Solution (Pty) Ltd | THLM/SCM24/2023-2024/AUD01 | Appointment of Audit firms for co-sourcing of internal audit projects for a period of 36 months | As per negotiated and accepted rates | 36 | 25/4/2024 | 24/4/2027 | None | R 0.00 | N/A | None | None | Active
159 | Shininiza Holdings (Pty Ltd | THLM/SCM22/2023-2024/W06 | Appointment of a panel of service providers for the supply and delivery of water and sanitation materials for a period of 36 months | As per negotiated and accepted rates | 36 | 17/5/2024 | 16/5/2027 | None | 540499.04 | N/A | None | None | Active
160 | Senzazona (Pty) Ltd | THLM/SCM22/2023-2024/W06 | Appointment of a panel of service providers for the supply and delivery of water and sanitation materials for a period of 36 months | As per negotiated and accepted rates | 36 | 17/5/2024 | 16/5/2027 | None | 29310 | N/A | None | None | Active
161 | Ramak Holdings (Pty) Ltd | THLM/SCM22/2023-2024/W06 | Appointment of a panel of service providers for the supply and delivery of water and sanitation materials for a period of 36 months | As per negotiated and accepted rates | 36 | 17/5/2024 | 16/5/2027 | None | R 0.00 | N/A | None | None | Active
162 | Pinpetty Investment (Pty) Ltd | THLM/SCM22/2023-2024/W06 | Appointment of a panel of service providers for the supply and delivery of water and sanitation materials for a period of 36 months | As per negotiated and accepted rates | 36 | 17/5/2024 | 16/5/2027 | None | 369535.5 | N/A | None | None | Active
163 | Masemanku Trading and Projects | THLM/SCM22/2023-2024/W06 | Appointment of a panel of service providers for the supply and delivery of water and sanitation materials for a period of 36 months | As per negotiated and accepted rates | 36 | 17/5/2024 | 16/5/2027 | None | 289730.44 | N/A | None | None | Active
164 | KMS Promotions and Restaurant (Pty) Ltd | THLM/SCM22/2023-2024/W06 | Appointment of a panel of service providers for the supply and delivery of water and sanitation materials for a period of 36 months | As per negotiated and accepted rates | 36 | 17/5/2024 | 16/5/2027 | None | R 0.00 | N/A | None | None | Active
165 | Thandi Elizabeth Retails (Pty) Ltd | THLM/SCM22/2023-2024/W06 | Appointment of a panel of service providers for the supply and delivery of water and sanitation materials for a period of 36 months | As per negotiated and accepted rates | 36 | 17/5/2024 | 16/5/2027 | None | R 0.00 | N/A | None | None | Active
166 | Keresi Trading Enterprise (Pty) Ltd | THLM/SCM22/2023-2024/W06 | Appointment of a panel of service providers for the supply and delivery of water and sanitation materials for a period of 36 months | As per negotiated and accepted rates | 36 | 17/5/2024 | 16/5/2027 | None | R 0.00 | N/A | None | None | Active
167 | Amathaka (Pty) Ltd | THLM/SCM22/2023-2024/W06 | Appointment of a panel of service providers for the supply and delivery of water and sanitation materials for a period of 36 months | As per negotiated and accepted rates | 36 | 17/5/2024 | 16/5/2027 | None | R 0.00 | N/A | None | None | Active
168 | Izumnandi (Pty) Ltd | THLM/SCM22/2023-2024/W06 | Appointment of a panel of service providers for the supply and delivery of water and sanitation materials for a period of 36 months | As per negotiated and accepted rates | 36 | 17/5/2024 | 16/5/2027 | None | R 0.00 | N/A | None | None | Active
169 | Tshedza Tshashu Industries | THLM/SCM026/2023-2024/CS02 | Appointment of a panel of advertising agencies to handle advertisement and other articles for thembisisle hani local municipality for a period of 36 months | As per negotiated and accepted rates | 36 | 2024-10-06 | 2027-09-06 | None | 128675.34 | N/A | None | None | Active
170 | Explohill Advertising and Media | THLM/SCM026/2023-2024/CS02 | Appointment of a panel of advertising agencies to handle advertisement and other articles for thembisisle hani local municipality for a period of 36 months | As per negotiated and accepted rates | 36 | 2024-10-06 | 2027-09-06 | None | 58090 | N/A | None | None | Active
171 | Thlabane Business Solutions | THLM/SCM026/2023-2024/CS02 | Appointment of a panel of advertising agencies to handle advertisement and other articles for thembisile hani local municipality for a period of 36 months | As per negotiated and accepted rates | 36 | 2024-10-06 | 2027-09-06 | None | 156515 | N/A | None | None | Active
172 | Namgwena Multi Projects (Pty) Ltd | THLM/SCM3/2023-2024/PED02 | Appointment of a panel of service providers for the supply and delivery of tools of trade for small medium and micro enterprises (SMME's) for a period of 12 months | As per negotiated and accepted rates | 12 | 18/6/2024 | 17/6/2025 | None | R 0.00 | N/A | None | None | Active
173 | Mandla Kasokobe General Trading | THLM/SCM3/2023-2024/PED04 | Appointment of a panel of service providers for the supply and delivery of tools of trade for small medium and micro enterprises (SMME's) for a period of 12 months | As per negotiated and accepted rates | 12 | 18/6/2024 | 17/6/2025 | None | R | N/A | None | None | Active
174 | Innovation Government Software Solution | THLM/SCM27/2023-2024/MM01 | Appointment of a service provider for the provision of E-PMS AND E-Risk systems for a period of 36 months | R 6 081 030.10 (Including 15% VAT) | 36 | 15/7/2024 | 14/7/2027 | None | 403564.44 | N/A | None | None | Active
175 | New Deal Engineering | THLM/SCM12/2023-2024/ICT01 | Appointment of an accredited service provider for the repairs and maintenance of THLM for a period of 36 months | R 2 496 323.43 (Excluding 15% VAT) | 36 | 18/7/2024 | 17/7/2027 | None | R 0.00 | N/A | None | None | Active
176 | Muratho Laboratory Service and Consulting | THLM/SCM23/2023-2024/WS07 | Appointment of service provider for the provision of laboratory services for monitoring of water and wastewater quality for a period of 36 months | R 3 183 283.54 (Excluding 15% VAT) and Disbursements | 36 | 31/7/2024 | 30/7/2027 | None | 423119.27 | N/A | None | None | Active
177 | Stickson General Trading | THLM/SCM11/2023-2024/R-02 | Construction of Verena C Bus and Taxi Route – Ward 11 | R 40 675 788.51 (Including 15% VAT) | 8 | 21/8/2024 | 20/04/2025 | None | 1312688.03 | N/A | None | None | Active
178 | Mamolato Construction and projects | THLM/SCM09/2023-2024/R01 | Appointment of a contractor for the construction of Tweefontein E bus route, ward 15, | R 11 095 410.19 (Including 15% VAT) | 12 | 28/8/2024 | 27/8/2025 | None | 680880.18 | N/A | None | None | Active
180 | Qubekelaphambile Construction | THLM/SCM29/2022-2023/WS03 | Appointment of a panel of contractors for rehabilitation, refurbishment and maintenance of water infrastructure for a period of 36 months(RRM & Boreholes) | As per negotiated rates | 36 | 16/10/2024 | 15/10/2027 | None | 10401106 | N/A | None | None | Active
181 | Snapppy Investment | THLM/SCM29/2022-2023/WS03 | Appointment of a panel of contractors for rehabilitation, refurbishment and maintenance of water infrastructure for a period of 36 months(RRM & Asberstos) | As per negotiated rates | 36 | 09/10/2024 | 08/10/2027 | None | 9776701.37 | N/A | None | None | Active
182 | Cwengisa Business Enterprise | THLM/SCM29/2022-2023/WS03 | Appointment of a panel of contractors for rehabilitation, refurbishment and maintenance of water infrastructure for a period of 36 months(RRM & Boreholes) | As per negotiated rates | 36 | 16/10/2024 | 15/10/2027 | None | 4682136.69 | N/A | None | None | Active
183 | Ulwazilwethu Trading Enterprise | THLM/SCM38/2023-2024/R-04 | Upgrade Sun City A Bus Route from Gravel to Paved – Ward 19 | R 11 266 961.59 including Contingencies and Value Added Tax (VAT) | 36 | 21/10/2024 | 24/08/2025 | None | 672750 | N/A | None | None | Active
184 | Lesedi La Balomo | THLM/SCM37/2023-2024/ SSD04 | Appointment of a panel of contractors for Refurbishment, Repairs and Maintenance of Municipal Buildings for a Period of 36 Months as and when required | As per negotiated rates | 36 | 25/10/2024 | 24/10/2027 | None | R0.00 | N/A | None | None | Active
185 | M90 Projects (Pty) Ltd | THLM/SCM37/2023-2024/ SSD04 | Appointment of a panel of contractors for Refurbishment, Repairs and Maintenance of Municipal Buildings for a Period of 36 Months as and when required | As per negotiated rates | 36 | 25/10/2024 | 24/10/2027 | None | R0.00 | N/A | None | None | Active
186 | Maesh (Pty) Ltd | THLM/SCM37/2023-2024/ SSD04 | Appointment of a panel of contractors for Refurbishment, Repairs and Maintenance of Municipal Buildings for a Period of 36 Months as and when required | As per negotiated rates | 36 | 25/10/2024 | 24/10/2027 | None | R0.00 | N/A | None | None | Active
187 | Shiela and Katlego’s Construction and Projects CC | THLM/SCM37/2023-2024/ SSD04 | Appointment of a panel of contractors for Refurbishment, Repairs and Maintenance of Municipal Buildings for a Period of 36 Months as and when required | As per negotiated rates | 36 | 25/10/2024 | 24/10/2027 | None | R0.00 | N/A | None | None | Active
188 | Yazo Mabusa Besana Construction and Projects | THLM/SCM37/2023-2024/ SSD04 | Appointment of a panel of contractors for Refurbishment, Repairs and Maintenance of Municipal Buildings for a Period of 36 Months as and when required | As per negotiated rates | 36 | 25/10/2024 | 24/10/2027 | None | R0.00 | N/A | None | None | Active
189 | OMKM Trading and Projects (Pty) Ltd | THLM/SCM31/2023-2024/C05 | Appointment of a service provider for the supply and delivery of stationery as and when required for the municipality | As per negotiated rates | 36 | 11/10/2024 | 10/10/2027 | None | 0 | N/A | None | None | Active
190 | Eyasekhethe Building Construction and Projects | THLM/SCM31/2023-2024/C05 | Appointment of a service provider for the supply and delivery of stationery as and when required for the municipality | As per negotiated rates | 36 | 11/10/2024 | 10/10/2027 | None | 0 | N/A | None | None | Active
191 | Guquphenduke Trading Enterprise | THLM/SCM31/2023-2024/C05 | Appointment of a service provider for the supply and delivery of stationery as and when required for the municipality | As per negotiated rates | 36 | 11/10/2024 | 10/10/2027 | None | 0 | N/A | None | None | Active
191 | Yakusoku Holdings (Pty) Ltd | THLM/SCM31/2023-2024/C05 | Appointment of a service provider for the supply and delivery of stationery as and when required for the municipality | As per negotiated rates | 36 | 11/10/2024 | 10/10/2027 | None | 0 | N/A | None | None | Active
193 | Yazo Mabusa Besana Construction & Projects | THLM/SCM38/2023-2024/R-04 | Appointment of a Panel of Service Providers for the Refurbishment, Repairs and Maintenance of Municipal Buildings for a period of 36 months. | As per negotiated rates | 36 | 25/10/2024 | 24/10/2027 | None | 0 | N/A | None | None | Active
194 | Maesh (Pty) Ltd | THLM/SCM38/2023-2024/R-04 | Appointment of a Panel of Service Providers for the Refurbishment, Repairs and Maintenance of Municipal Buildings for a period of 36 months. | As per negotiated rates | 36 | 25/10/2024 | 24/10/2027 | None | 0 | N/A | None | None | Active
195 | M90 Project (Pty) Ltd | THLM/SCM38/2023-2024/R-04 | Appointment of a Panel of Service Providers for the Refurbishment, Repairs and Maintenance of Municipal Buildings for a period of 36 months. | As per negotiated rates | 36 | 25/10/2024 | 24/10/2027 | None | 0 | N/A | None | None | Active
196 | Shiela and Katlego's Construction and Preojects CC | THLM/SCM38/2023-2024/R-04 | Appointment of a Panel of Service Providers for the Refurbishment, Repairs and Maintenance of Municipal Buildings for a period of 36 months. | As per negotiated rates | 36 | 25/10/2024 | 24/10/2027 | None | 0 | N/A | None | None | Active
197 | Lesedi La Balomo (Pty) Ltd | THLM/SCM38/2023-2024/R-04 | Appointment of a Panel of Service Providers for the Refurbishment, Repairs and Maintenance of Municipal Buildings for a period of 36 months. | As per negotiated rates | 36 | 25/10/2024 | 24/10/2027 | None | 0 | N/A | None | None | Active
198 | GPTN Trading CC | THLM/SCM034/ 2023-2024/WS09 | Appointment of a contractor for the upgrading of Tweefontein K waste water treatment works (WWTW) PHASE 3 | R 33 590 882.64 | 18 | 07/11/2024 | 06/04/2026 | None | 0 | N/A | None | None | Active
199 | Gold Heart trading | THLM/SCM03/2024-2025/ICT 01 | Appointment of a service provider for the Leasing and Maintenance of printing services and other related products for a period of 36 Months | R 2 966 584.93 | 36 | 22/11/2024 | 21/11/2027 | None | 0 | N/A | None | None | Active
200 | Botle Training Academy | THLM/SCM01/2024-2025/HR01/01 | Appointment of a Panel of Service Providers for skills development training of municipal employees and councillors for a period of 36 months. | As per negotiated rates | 36 | 22/11/2024 | 21/1/2027 | None | 0 | N/A | None | None | Active
201 | Matabane Professional Accountants (Pty) Ltd | THLM/SCM01/2024-2025/HR01/01 | Appointment of a Panel of Service Providers for skills development training of municipal employees and councillors for a period of 36 months. | As per negotiated rates | 36 | 22/11/2024 | 21/1/2027 | None | 0 | N/A | None | None | Active
202 | Gosele Consulting and Projects (Pty) Ltd | THLM/SCM01/2024-2025/HR01/01 | Appointment of a Panel of Service Providers for skills development training of municipal employees and councillors for a period of 36 months. | As per negotiated rates | 36 | 22/11/2024 | 21/1/2027 | None | 0 | N/A | None | None | Active
203 | Twinmark Strategy and Management Consultants (Pty) Ltd | THLM/SCM01/2024-2025/HR01/01 | Appointment of a Panel of Service Providers for skills development training of municipal employees and councillors for a period of 36 months. | As per negotiated rates | 36 | 22/11/2024 | 21/1/2027 | None | 0 | N/A | None | None | Active
204 | Nsukay Trading and Projects | THLM/SCM01/2024-2025/HR01/01 | Appointment of a Panel of Service Providers for skills development training of municipal employees and councillors for a period of 36 months. | As per negotiated rates | 36 | 22/11/2024 | 21/1/2027 | None | 0 | N/A | None | None | Active
205 | Mandla Kasokobe General Trading (Pty) Ltd | THLM/SCM07/2024-2025/SS01 | Upgrading of Solomon Mahlangu (KwaMhlanga) Stadium, Phase 2 | R8 169 340.70 | 36 | 28/11/2024 | 27/1/2027 | None | 0 | N/A | None | None | Active

## EXPIRING WITHIN 6 MONTHS
CONTRACT REGISTER AS AT 31 DECEMBER 2024
No | Name of Service Provider | Bid/ Contract Number | Description of Service | Contract Amount | Contract Period | Start Date | End Date | Extension | Expenditure | Variation | Penalties Paid by Municipality / Impose by or Contractor | Contract Ammendment Date | Comment
5 | Fast Moving Trading T/A Uhhiya | THLM/SCM02/2021-2022/BTO02 | Appointment for a proffessional service provider to provide data management solutions and verifications system for a period of 36 months | R2 277 000.00 (Incl. VAT) | 36 | 2022-03-01 | 2025-02-01 | N/A | 1075250 | None | None | None | Active (Project Expiring in 1 month)
6 | Databox Technologies | THLM/SCM07/2021-2022/CRS04 | Provision of leasing and maintenance of photocopier machines and supply and delivery of related products for a period of 36 months | R75 945.27 per month | 36 | 2022-03-01 | 2025-02-01 | N/A | 3650295.73 | None | None | None | Active (Project Expiring in 1 month)
Formulas:
Start Date = [Start Date, row above]
End Date = [End Date, row above]

## EXPIRED CONTRACTS
CONTRACT REGISTER AS AT 31 DECEMBER 2024
No | Name of Service Provider | Bid/ Contract Number | Description of Service | Contract Amount | Contract Period | Start Date | End Date | Extension | Expenditure | Variation | Penalties Paid by Municipality / Impose by or Contractor | Contract Ammendment Date | Comment
1 | Mpumamanzi | THLM/PW01/2016-2019 | Accredited laboratory for sampling and analysis of water | As per proposed rates | 36 | 14/4/2021 | 13/4/2024 | 14/7/2024 | 4205550.2 | None | None | None | Contract Expired
1 | Qubekelaphambile Construction and Projects | THLM/SCM04/2023-2024/WS01 | Upgrading of Sheldon Water Infrastructure- Ward 14 | R 11 280 215.22 including Contingencies and Value Added Tax (VAT). | 10 | 2024-11-01 | 2024-10-11 | N/A | 2594268.38 | None | None | None | Contract Expired
2 | LMK Mngoni Group (Pty) Ltd T/A LMK Consulting | THLM/SCM07/01/2021-2022/BTO01 | Appointment for a panel of service providers to provide financial advisory and debt collection services for a period of 36 months | Based on quoted rates of 14.25% | 36 | 30/12/2021 | 29/12/2024 | N/A | R 6 721 538.63 | None | None | None | Contract Expired
3 | Noko Maimela Incorporated | THLM/SCM07/01/2021-2022/BTO02 | Appointment for a panel of service providers to provide financial advisory and debt collection services for a period of 36 months | Based on quoted rates of 10% | 36 | 30/12/2021 | 29/12/2024 | N/A | R0.00 | None | None | None | Contract Expired
4 | Double Medprac Solutions | THLM/SCM07/01/2021-2022/BTO03 | Appointment for a panel of service providers to provide financial advisory and debt collection services for a period of 36 months | Based on quoted rates of 10.5% | 36 | 30/12/2021 | 29/12/2024 | N/A | R0.00 | None | None | None | Contract Expired