## Sheet1
CONSOLIDATED PROCUREMENT PLAN PROGRESS AS AT 30 SEPTEMBER 2023
Item no | Description of goods / services / Infrastructure project | Estimated value (including all applicable taxes) | Envisaged date of advertisement in the website, newspapers or other media | Envisaged closing date of bid | Envisaged date of award | Progress | Management Comment
1 | Water Sample Testing | R 1 080 000.00 | 2023-12-03 | 2024-01-26 | 2024-04-30 | Still to be implemented | The specifications were submitted to the Head of Department for review before submission to the BSC
2 | Panel of Town planners | R 700 000.00 | 2023-08-30 | 2023-09-29 | 2023-12-15 | Still to be implemented | Specification committee dealt with the project on 11th September 2023 and the report was submitted on the 29th September 2023.
3 | Panel of service providers to provide temporary water supply through water tankers within Thembisile Hani Local Municipality as and when required for a period of 36 months | R3 500 000.00 | 2023-06-24 | 2023-07-15 | 2023-10-15 | Evaluation Stage | Project is at evaluation stage
28 | Provision for security services | R 26 000 000,00 | 2023-07-01 | 2023-07-26 | 2023-11-05
29 | Supply, Install and Maintenance of council chamber recoding system for 24 months as and when required. | R650,000.00 | 2023-07-16 | 2023-08-16 | 2023-09-16
30 | Alternative Sanitation System | R1,000,000.00 | 2023-05-10 | 2023-06-19 | 2023-08-18
31 | Construction of Phola Park and Taxi Road WP2 (Intersection) | R12,736,844.13 | 2023-05-10 | 2023-06-19 | 2023-08-18
32 | Constrution of Verena C bus Route | R29,214,500 | 2023-05-10 | 2023-06-19 | 2023-08-18
4 | Construction of Tweefontein E Bus Route | R13 047 760.28 | 2023-08-13 | 2023-09-20 | 2023-11-30 | Specification Aproved | Project was advertised on the 29th September 2023
5 | Construction of Verena A- D Bus Route | R 48 995 773.53 | 2023-08-13 | 2023-09-20 | 2023-11-30 | Specification finalised awaiting approval | Project was advertised on the 29th September 2023
6 | Construction of Verena Water Infrastructure | R 33 613 056.75 | 2023-08-20 | 2028-09-26 | 2023-12-15 | Specification Aproved | Project awaiting evaluation
7 | Thembalethu Water Infrastructure | R 31 336 731.00 | 2023-08-27 | 2023-10-04 | 2023-12-15 | Specification Aproved | Projects closed and awaiting evaluation
8 | Rehabilitation of Boreholes | R 40 966 474.00 | 2023-08-27 | 2023-10-04 | 2023-12-15 | Still to be implemented | Specification declined project to be allocated under the Water Infrastructure project.
9 | Refurbishment of Oxidation Ponds - Phase 2 | R 4 613 020.00 | 2023-09-10 | 2023-09-27 | 2023-11-30 | Still to be implemented | Project approved by DWS. Scoping report completed.PDR compiled and DDR in progress.
10 | Upgrading of Tweefontein K WWTW - Phase 3 | R16 000 000.00 | 2023-08-27 | 2023-10-04 | 2023-12-15 | Still to be implemented | Project approved by DWS. Scoping report completed.PDR compiled and DDR in progress.
11 | Construction of Sun City A road | R6 500 000.00 | 2023-08-27 | 2023-09-21 | 2023-11-30 | Still to be implemented | PDR Completed. SP currently busy DDR.
12 | Installation of Telemetry System | R 9 500 000.00 | 2023-08-27 | 2023-09-23 | 2023-11-30 | Still to be implemented | Project included in the ICT project of Maputunuka (Project to be dealt with during the review of the plan)
13 | Construction of Verena C Bus Route | R 28 500 000.00 | 2023-09-10 | 2023-10-20 | 2023-12-15 | Still to be implemented | Projects was advertised on the 29th September 2023
14 | Construction of Water Reticulation at Sheldon -Ward 14 | R10 500 000.00 | 2023-08-06 | 2023-10-20 | 2023-12-15 | Specification Aproved | Project closed and awaiting evaluation
15 | Alternative Sanitation System | R1 000 000.00 | 2024-01-15 | 2024-02-20 | 2024-05-30 | Still to be implemented | Project not approved by COGTA
16 | Construction of Multi-Purpose Centre in Phumula (Multi-Year Project) - Ward 23 | R 19 131 667.45 | 2023-09-10 | 2023-10-26 | 2023-12-15 | Still to be implemented | Project approved and design in the process of reviewal. The process of reviewal is progress
17 | Construction of Multi-Purpose Centre in Moloto North (Multi-Year Project) - Ward 2 | R 9 065 328.08 | 2023-09-10 | 2023-10-20 | 2023-12-15 | Still to be implemented | Project approved and design in the process of reviewal. The process of reviewal is progress
18 | Procurement of Machinery For Landfill site | R 5 481 000.00 | 2023-09-10 | 2023-10-20 | 2023-12-15 | Still to be implemented | Specification concluded and submitted for approval on the 29th September 2023
19 | Construction of Pedestrian Bridges - Ward 32 -4( Zakheni to Kwamhlanga | R 16 998 953.00 | 2023-09-10 | 2023-10-23 | 2024-01-15 | Specification Approved | Project location to be reviewed (Now the project is implemented by public works under Welisizwe Programme).
20 | Construction of Mzimuhle Water Infrastructure | R11 680 616.00 | 2023-09-10 | 2023-10-24 | 2024-01-16 | Still to be implemented | Project not approved by DWS. Follow up has been made with DWS for fast tracking the process of approval of submitted Technical report.
21 | Appointment of a panel of service providers for training/ skills development for the municipality for a period of 36 months as and when required | R 650 000.00 | 2023-07-30 | 2023-08-18 | 2023-09-30 | Tender closed on 16th August 2023 | The project at evaluation stage
22 | Appointment of a panel of contractors for Rehabilitation,Refurbishment and Maintenance of Water and Sanitation infrastructure as and when required for a period of 36 months | R 22 500 000.00 | 2023-05-31 | 2023-07-13 | 2023-08-30 | Tender at evaluation stage | Project past evaluation and adjudication stages and awaiting final award
23 | Compilation and maintenance of the General Valuation Roll and Supplementary Valuation Roll for a period of 60 months | R 3 500 000.00 | 2023-04-30 | 2023-07-11 | 2023-08-30 | Tender at adjudication stage | Project appointed on the 30th August 2023
24 | Appointment of a service provider for job evaluation for the municipality for a period of 36 months as and when required | R 200 000.00 | 45168 | 45190 | 45290 | Project to be adverised before 30 August 2023 | Specification and tender document to be submitted. The RFQ to be issued by no later than 22nd September 2023
25 | Appointment of a service provider for electronic recruitment system for the municipality for recruitment purposes. | R 800 000.00 | 2023-10-15 | 2023-11-23 | 2024-01-30 | Still to be advertised | Awaiting specification from user-department
26 | Procurement for the provisioning and management of Electronic Document Management System | R 2 800 000.00 | 2023-08-30 | 2023-09-21 | 2023-12-30 | Still to be advertised | Specification concluded on the 29th September 2023 and awaiting final approval for publishing
27 | Appointment of a service provider for the supply and delivery of Stationery as and when required for the municipality | R 1 551 000.00 | 2024-01-24 | 2024-02-22 | 2024-05-30 | Still to be advertised | Specification to be submitted on 30th October 2023
28 | Appointment of a service provider for the supply and delivery Office Furniture as and when required for the municipality | R 650 000.00 | 2024-01-24 | 2024-02-22 | 2024-05-30 | Still to be advertised | Specification to be submitted on 30th October 2024
29 | Panel of audit firms for co-sourcing of internal audit projects for a period of 36 months | Based on quoted rates | 2023-12-31 | 2024-01-31 | 2024-03-31 | Still to be advertised | Specification to be submitted on 30th October 2025
30 | Purchase of SMME`s Equipment | R 5 000 000.00 | 2023-08-19 | 2024-09-24 | 2023-01-30 | Project not advertised | Specification to be submitted for the BSC sitting of 26th September 2023
31 | Tourism Celebration Day | R 800 000.00 | 2023-08-06 | 2023-08-22 | 2023-09-15 | Project not advertised | Project canceled by the department.The department proposed PPP which still has to follow proper processes
32 | Formulation of Tourism Brochure | R 200 000.00 | 2023-08-27 | 2023-09-28 | 2023-10-31 | Evaluation Stage | Evaluation concluded.Project awaiting final award
33 | Review of VAT Returns | R 3 000 .000 | 2023-08-19 | 2024-09-24 | 2023-01-30 | Tender not advertised | Specification still to be submitted
34 | Auction of Municipal Fleet | R 3 000.000 | 2023-10-26 | 2023-11-29 | 2024-02-15 | Still to be advertised | Specification still to be submitted
35 | Supply and delivery of Fuel for mucipal fleet | R 4 000 000 | 2023-08-19 | 2024-09-24 | 2023-01-30 | Tender not advertised | Tender closed on the 02nd October and at evaluation stage
36 | Supply and delivery of tyres and repairs of punctures | R 2 000 000 | 2023-09-17 | 24--Oct-24 | 2024-01-26 | Still to be advertised | Specification to be submitted and dealt with on the 10th October 2023
35 | Maintenance of yellow and white fleet | R 4 000 000 | 2023-08-19 | 2024-09-24 | 2023-01-30 | Project advertised | Specification to be submitted for the BSC sitting of 26th September 2023
36 | Provision of Insurance Services | R 3 000 .000 | 2023-10-22 | 2024-11-30 | 2024-01-25 | Still to be advertised | Specification to be submitted on the 15th of October 2023
37 | Maintenance of Kwaggafontein dumping site for 36 months as and when required | R 659 340.00 | 2023-10-22 | 2024-11-30 | 2024-01-25 | Still to be advertised | Specification concluded on the 29th September 2023 and awaiting final approval for publishing
38 | Supply and delivery of white and yellow plant parts | R 2 000 000.00 | 2023-10-22 | 2024-11-30 | 2024-01-25 | Still to be advertised | Specification to be submitted for the 15th of October 2023 BSC sitting
43 | E-Risk System | R 496 000.00 | 2023-10-29 | 2023-11-22 | 2024-02-28 | Still to be advertised | Specification to be submitted for the 15th of October 2023 BSC sitting
39 | EPMS | R 4 325 346.00 | 2023-10-29 | 2023-11-22 | 2024-02-28 | Still to be advertised | Specification to be submitted for the 15th of October 2023 BSC sitting
40 | Maintenance of Council Chamber | R644 208.00 | 2023-09-03 | 2023-09-28 | 2024-01-31 | Still to be advertised | Specification concluded on the 29th September 2023 and awaiting final approval for publishing
41 | Appointment of a service provider for the supply and delivery of Water and Sanitation materials as and when required for the municipality | R1 000 000.00 | 2023-08-27 | 2023-09-15 | 2024-12-15 | Still to be advertised | Specification to be submitted by the 15th October 2023
42 | Supply and delivery of Operational Full manaintenance lease | R42 000 000.00 | 2023-08-27 | 09-Nov-2-3 | 2023-12-15 | Project re-advertised | Tender closed on the 02nd October and at evaluation stage